## Phase 2 Program
Task Name | Workstream | Start Date | End Date | Duration | Status | Owner
Process development | CMC | 2026-01-05 | 2026-04-30 | 115 | Complete | Sarah
Analytical method qualification | CMC | 2026-02-01 | 2026-05-15 | 103 | Complete | Raj
Engineering runs | CMC | 2026-05-01 | 2026-07-31 | 91 | In Progress | Sarah
Process validation | CMC | 2026-06-01 | 2026-10-30 | 151 | In Progress | Sarah
Stability studies | CMC | 2026-07-01 | 2027-01-31 | 214 | At Risk | Raj
GMP release testing | CMC | 2026-11-01 | 2026-12-15 | 44 | Not Started | Raj
Drug product lot release | CMC | 2026-12-15 | 2026-12-15 | 0 | Not Started | Sarah
Protocol finalization | Clinical | 2026-02-01 | 2026-03-31 | 58 | Complete | Priya
IRB submissions | Clinical | 2026-04-01 | 2026-06-15 | 75 | In Progress | Priya
Site identification | Clinical | 2026-03-15 | 2026-05-30 | 76 | Complete | Tom
Site initiation visits | Clinical | 2026-06-01 | 2026-08-31 | 91 | Delayed | Tom
First site activated | Clinical | 2026-08-01 | 2026-08-01 | 0 | Delayed | Tom
First patient in | Clinical | 2026-09-01 | 2026-09-01 | 0 | Not Started | Priya
Enrollment | Clinical | 2026-09-01 | 2027-05-30 | 271 | Estimate | Priya
Last patient in | Clinical | 2027-05-30 | 2027-05-30 | 0 | Estimate | Priya
Top line data | Clinical | 2027-09-15 | 2027-09-15 | 0 | Estimate | Priya
Pre-IND meeting prep | Regulatory | 2026-01-15 | 2026-03-15 | 59 | Complete | Dana
Pre-IND meeting | Regulatory | 2026-03-20 | 2026-03-20 | 0 | Complete | Dana
IND writing | Regulatory | 2026-04-01 | 2026-08-31 | 152 | Blocked | Dana
IND submission | Regulatory | 2026-09-15 | 2026-09-15 | 0 | Not Started | Dana
30-day FDA review | Regulatory | 2026-09-16 | 2026-10-15 | 29 | Not Started | Dana
IND cleared | Regulatory | 2026-10-15 | 2026-10-15 | 0 | Not Started | Dana
IND-enabling tox studies | Nonclinical | 2026-01-01 | 2026-06-30 | 180 | Complete | Alex
Tox study reports | Nonclinical | 2026-05-15 | 2026-07-31 | 77 | In Progress | Alex
DMPK package | Nonclinical | 2026-03-01 | 2026-07-15 | 136 | At Risk | Alex
Comparator sourcing | Supply Chain | 2026-05-01 | 2026-08-30 | 121 | In Progress | Maria
Label and kit design | Supply Chain | 2026-06-01 | 2026-07-31 | 60 | Not Started | Maria
First patient kit delivery | Supply Chain | 2026-08-25 | 2026-08-25 | 0 | Estimate | Maria